## START HERE
STONE COLUMN - COST-PLUS ESTIMATE & PROGRESS BILLING
The budget creates the estimate. Actual QuickBooks job costs create the invoice.
STEP | WORKFLOW
1 | Complete Project Setup. Yellow cells are user inputs.
2 | Build the internal BUDGET by entering original budget, adjustments, discounts, descriptions, and billing flags.
3 | The ESTIMATE automatically summarizes that budget and adds the estimated management fee. It clearly states that figures are estimates only.
4 | Export the latest QuickBooks Job Estimates vs. Actuals report. Copy the entire Sheet1 report and paste it into QB JOB COST IMPORT beginning at cell A6.
5 | COST RECONCILIATION matches QuickBooks actual costs to the four-digit cost codes and subtracts costs already recorded in DRAW HISTORY.
6 | Review INVOICE and INVOICE DETAIL. The amount due is actual new cost plus the management fee, less any credit applied this draw.
7 | After sending the invoice, copy the Current Draw Cost column from COST RECONCILIATION and paste VALUES ONLY into the matching draw column in DRAW HISTORY.
8 | For the next draw, replace the QB import with the newest cumulative report, select the next draw number, and repeat.
CONTROL: Do not overwrite prior draw-history columns. That history is what prevents the same cumulative QuickBooks costs from being billed twice. Budget overruns are highlighted but remain billable under the cost-plus model.

## Project Setup
PROJECT SETUP
Company Name | STONE COLUMN CUSTOM HOMES + REMODELING
Payable To | Stone Column Properties, LLC.
Company Address | 7772 Turner Rd.
Company City / State / ZIP | Woodstock, GA 30188
Phone | (404) 867-7890
Email
Customer Name
Customer Address
Customer City / State / ZIP
Customer Email
Project Name
Project Address
Estimate #
Estimate Date
Management Fee % | 18%
Estimated Deposit % | 40%
Estimate Terms | Cost-plus arrangement. Budget amounts are estimates only. Owner is billed for actual project costs incurred plus the stated project-management fee.
CURRENT DRAW NUMBER | 1
Invoice # Prefix
Invoice Date
Due Date
Credit / Deposit Applied This Draw | 0
Payment Terms | Due upon receipt

## BUDGET
INTERNAL COST-PLUS PROJECT BUDGET
Yellow = input ¦ Blue = calculated ¦ Budget is an estimate and does not cap reimbursable actual cost
Code | Activity | Original Budget | Description / Scope | Adjustment | Reason | Vendor Discount | Adjusted Budget | Include in Estimate? | Billable Cost? | Division | Current QB Actual | Prior Billed | Current Draw Cost | Budget Variance | Status
1010 | Plan / Site Plans | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Preconstruction & General | 0 | 0 | 0 | 0 | OK
1011 | Permits/Fees/Water/Sewer | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Preconstruction & General | 0 | 0 | 0 | 0 | OK
1020 | Surveys | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Preconstruction & General | 0 | 0 | 0 | 0 | OK
1070 | Builders Risk Insurance | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Preconstruction & General | 0 | 0 | 0 | 0 | OK
1080 | Reinspection Fees | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Preconstruction & General | 0 | 0 | 0 | 0 | OK
2010 | Grading - Clear Lot | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Sitework | 0 | 0 | 0 | 0 | OK
2011 | Grading - Haul Debris | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Sitework | 0 | 0 | 0 | 0 | OK
2012 | Grading - Cut Foundation | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Sitework | 0 | 0 | 0 | 0 | OK
2013 | Grading - Backfill Found | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Sitework | 0 | 0 | 0 | 0 | OK
2014 | Grading - Cut Drive | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Sitework | 0 | 0 | 0 | 0 | OK
2015 | Grading - Final | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Sitework | 0 | 0 | 0 | 0 | OK
2016 | Grading - Misc | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Sitework | 0 | 0 | 0 | 0 | OK
2021 | Retaining Walls - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Sitework | 0 | 0 | 0 | 0 | OK
2030 | Erosion Control | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Sitework | 0 | 0 | 0 | 0 | OK
2031 | Gravel | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Sitework | 0 | 0 | 0 | 0 | OK
3005 | Pump Concrete | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Foundation | 0 | 0 | 0 | 0 | OK
3010 | Footing - Material | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Foundation | 0 | 0 | 0 | 0 | OK
3011 | Footing - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Foundation | 0 | 0 | 0 | 0 | OK
3020 | Block - Materials | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Foundation | 0 | 0 | 0 | 0 | OK
3021 | Block - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Foundation | 0 | 0 | 0 | 0 | OK
3031 | Slab - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Foundation | 0 | 0 | 0 | 0 | OK
3050 | Foundation Wall - Material | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Foundation | 0 | 0 | 0 | 0 | OK
3051 | Foundation Wall - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Foundation | 0 | 0 | 0 | 0 | OK
3070 | Termite Treat Soil | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Foundation | 0 | 0 | 0 | 0 | OK
3080 | Waterproof Foundation | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Foundation | 0 | 0 | 0 | 0 | OK
3090 | Engineering | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Foundation | 0 | 0 | 0 | 0 | OK
3095 | Water Lines - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Foundation | 0 | 0 | 0 | 0 | OK
3096 | Sewer Lines - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Foundation | 0 | 0 | 0 | 0 | OK
4010 | Brick - Materials | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4011 | Brick - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4020 | Stone - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4021 | Stucco - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4030 | Framing - Material | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4031 | Framing - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4032 | Floor Screw - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4040 | Trusses - Material | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4041 | Steel Beams | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4050 | Windows/Ex Doors - Mat | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4051 | Windows/Ex Doors - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4060 | Skylight - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4061 | Specialty Glass - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4070 | Roofing - Material | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4071 | Roofing - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4080 | Plumbing - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4082 | Plumbing - Fixtures | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4085 | Electrical - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4086 | Low Voltage - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4090 | HVAC - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4100 | Pre-Fab Fireplace - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4110 | Trash Removal - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4120 | Deck - Materials | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4121 | Deck - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4130 | Front Porch - Mat | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4131 | Front Porch - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4140 | Siding/Cornice - Mat | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4141 | Siding/Cornice - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4145 | Flashing - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4150 | Cedar Shingles - Mat | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4151 | Cedar Shingles - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4170 | Shutters | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4180 | Insulation - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4190 | Flower Box - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
4200 | Housewrap - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Structure, Exterior & MEP | 0 | 0 | 0 | 0 | OK
5010 | Sheetrock - Materials | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5011 | Sheetrock - Sub *** | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5020 | Garage Doors - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5030 | Drive/Walk/Patio - M | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5031 | Drive/Walk/Patio - S | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5035 | Public Walks - Conc | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5036 | Public Walks - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5045 | Lockout - Materials | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5046 | Lockout - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5049 | Trim - Materials | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5050 | Trim -Int Doors - Mat | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5051 | Trim - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5055 | Stair Parts - Mat | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5060 | Gutters - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5065 | Metal Roof - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5070 | Cabinets - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5075 | Countertops - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5080 | Paint - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5090 | Sinks / Tubs | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5095 | Cultured Marble - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5100 | Fireplace Veneer - Mat | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5101 | Fireplace Veneer - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5111 | Ceramic Tile - Sub *** | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5130 | Hardware/Supplies | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5140 | Mirrors/Ecl/Shlve - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5150 | Light Fixtures | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5160 | Appliances - Material | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5170 | Hardwoods - Sub *** | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5180 | Vinyl Flooring - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5190 | Carpet Flooring - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5200 | Screens - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5220 | Mailbox - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5230 | Wrought Iron - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5240 | Tub/Sink Repair - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
5270 | Elevator - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Interior Finishes | 0 | 0 | 0 | 0 | OK
6040 | Irrigation System - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Exterior Improvements & Closeout | 0 | 0 | 0 | 0 | OK
6050 | Landscape - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Exterior Improvements & Closeout | 0 | 0 | 0 | 0 | OK
6060 | Fence | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Exterior Improvements & Closeout | 0 | 0 | 0 | 0 | OK
6070 | Window Clean - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Exterior Improvements & Closeout | 0 | 0 | 0 | 0 | OK
6080 | Interior Clean - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Exterior Improvements & Closeout | 0 | 0 | 0 | 0 | OK
6090 | Carpet Clean - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Exterior Improvements & Closeout | 0 | 0 | 0 | 0 | OK
6100 | Pressure Wash - Sub | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Exterior Improvements & Closeout | 0 | 0 | 0 | 0 | OK
6110 | Labor Cleanup / Punchout | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Exterior Improvements & Closeout | 0 | 0 | 0 | 0 | OK
7025 | Utilities - Water/Sewer | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Other Project Costs | 0 | 0 | 0 | 0 | OK
7050 | Pool, pavers, Fence | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Other Project Costs | 0 | 0 | 0 | 0 | OK
7055 | Interior Upgrades | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Other Project Costs | 0 | 0 | 0 | 0 | OK
7060 | Exterior Upgrades | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Other Project Costs | 0 | 0 | 0 | 0 | OK
7080 | Design Fee | 0 |  | 0 |  | 0 | 0 | Yes | Yes | Other Project Costs | 0 | 0 | 0 | 0 | OK
7082 | Sales Commission | 0 |  | 0 |  | 0 | 0 | Yes | No | Other Project Costs | 0 | 0 | 0 | 0 | EXCLUDED
9999 | Transfer WIP to CGS | 0 |  | 0 |  | 0 | 0 | Yes | No | Other Project Costs | 0 | 0 | 0 | 0 | EXCLUDED
[5 empty] | ESTIMATED BILLABLE HARD COST |  | 0
[5 empty] | ESTIMATED MANAGEMENT FEE |  | 0
[5 empty] | ESTIMATED PROJECT TOTAL |  | 0

## QB JOB COST IMPORT
QUICKBOOKS JOB COST IMPORT - CUMULATIVE ACTUALS
Replace the prior import each draw. Copy the entire QuickBooks exported Sheet1 and paste beginning at A6. Keep the QuickBooks Service in column C and Actual Cost in column F. Column I parses the cost code automatically.
Parsed Cost Code
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## COST RECONCILIATION
COST RECONCILIATION - BUDGET VS. QUICKBOOKS VS. PRIOR DRAWS
Code | Activity | Adjusted Budget | Current QB Actual | Previously Invoiced Cost | Current Draw Cost | Actual vs Budget | Billable? | Import Match | Review
1010 | Plan / Site Plans | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
1011 | Permits/Fees/Water/Sewer | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
1020 | Surveys | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
1070 | Builders Risk Insurance | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
1080 | Reinspection Fees | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
2010 | Grading - Clear Lot | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
2011 | Grading - Haul Debris | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
2012 | Grading - Cut Foundation | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
2013 | Grading - Backfill Found | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
2014 | Grading - Cut Drive | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
2015 | Grading - Final | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
2016 | Grading - Misc | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
2021 | Retaining Walls - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
2030 | Erosion Control | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
2031 | Gravel | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
3005 | Pump Concrete | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
3010 | Footing - Material | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
3011 | Footing - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
3020 | Block - Materials | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
3021 | Block - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
3031 | Slab - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
3050 | Foundation Wall - Material | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
3051 | Foundation Wall - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
3070 | Termite Treat Soil | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
3080 | Waterproof Foundation | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
3090 | Engineering | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
3095 | Water Lines - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
3096 | Sewer Lines - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4010 | Brick - Materials | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4011 | Brick - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4020 | Stone - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4021 | Stucco - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4030 | Framing - Material | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4031 | Framing - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4032 | Floor Screw - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4040 | Trusses - Material | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4041 | Steel Beams | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4050 | Windows/Ex Doors - Mat | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4051 | Windows/Ex Doors - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4060 | Skylight - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4061 | Specialty Glass - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4070 | Roofing - Material | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4071 | Roofing - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4080 | Plumbing - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4082 | Plumbing - Fixtures | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4085 | Electrical - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4086 | Low Voltage - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4090 | HVAC - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4100 | Pre-Fab Fireplace - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4110 | Trash Removal - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4120 | Deck - Materials | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4121 | Deck - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4130 | Front Porch - Mat | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4131 | Front Porch - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4140 | Siding/Cornice - Mat | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4141 | Siding/Cornice - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4145 | Flashing - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4150 | Cedar Shingles - Mat | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4151 | Cedar Shingles - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4170 | Shutters | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4180 | Insulation - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4190 | Flower Box - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
4200 | Housewrap - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5010 | Sheetrock - Materials | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5011 | Sheetrock - Sub *** | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5020 | Garage Doors - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5030 | Drive/Walk/Patio - M | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5031 | Drive/Walk/Patio - S | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5035 | Public Walks - Conc | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5036 | Public Walks - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5045 | Lockout - Materials | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5046 | Lockout - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5049 | Trim - Materials | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5050 | Trim -Int Doors - Mat | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5051 | Trim - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5055 | Stair Parts - Mat | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5060 | Gutters - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5065 | Metal Roof - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5070 | Cabinets - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5075 | Countertops - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5080 | Paint - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5090 | Sinks / Tubs | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5095 | Cultured Marble - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5100 | Fireplace Veneer - Mat | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5101 | Fireplace Veneer - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5111 | Ceramic Tile - Sub *** | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5130 | Hardware/Supplies | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5140 | Mirrors/Ecl/Shlve - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5150 | Light Fixtures | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5160 | Appliances - Material | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5170 | Hardwoods - Sub *** | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5180 | Vinyl Flooring - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5190 | Carpet Flooring - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5200 | Screens - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5220 | Mailbox - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5230 | Wrought Iron - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5240 | Tub/Sink Repair - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
5270 | Elevator - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
6040 | Irrigation System - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
6050 | Landscape - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
6060 | Fence | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
6070 | Window Clean - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
6080 | Interior Clean - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
6090 | Carpet Clean - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
6100 | Pressure Wash - Sub | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
6110 | Labor Cleanup / Punchout | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
7025 | Utilities - Water/Sewer | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
7050 | Pool, pavers, Fence | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
7055 | Interior Upgrades | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
7060 | Exterior Upgrades | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
7080 | Design Fee | 0 | 0 | 0 | 0 | 0 | Yes | NO COST / NO BUDGET | OK
7082 | Sales Commission | 0 | 0 | 0 | 0 | 0 | No | NO COST / NO BUDGET | OK
9999 | Transfer WIP to CGS | 0 | 0 | 0 | 0 | 0 | No | NO COST / NO BUDGET | OK
BILLABLE TOTALS |  | 0 | 0 | 0 | 0 | 0

## DRAW HISTORY
DRAW HISTORY - INVOICED ACTUAL COST BY COST CODE
After sending an invoice, paste VALUES ONLY from COST RECONCILIATION Current Draw Cost into the corresponding draw column below.
Code | Activity | Draw 1 | Draw 2 | Draw 3 | Draw 4 | Draw 5 | Draw 6 | Draw 7 | Draw 8 | Draw 9 | Draw 10
1010 | Plan / Site Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1011 | Permits/Fees/Water/Sewer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1020 | Surveys | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070 | Builders Risk Insurance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1080 | Reinspection Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2010 | Grading - Clear Lot | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011 | Grading - Haul Debris | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2012 | Grading - Cut Foundation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2013 | Grading - Backfill Found | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2014 | Grading - Cut Drive | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015 | Grading - Final | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2016 | Grading - Misc | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021 | Retaining Walls - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2030 | Erosion Control | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2031 | Gravel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3005 | Pump Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3010 | Footing - Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3011 | Footing - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3020 | Block - Materials | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3021 | Block - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3031 | Slab - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3050 | Foundation Wall - Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3051 | Foundation Wall - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3070 | Termite Treat Soil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3080 | Waterproof Foundation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3090 | Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3095 | Water Lines - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3096 | Sewer Lines - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010 | Brick - Materials | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4011 | Brick - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4020 | Stone - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4021 | Stucco - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4030 | Framing - Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4031 | Framing - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4032 | Floor Screw - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4040 | Trusses - Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4041 | Steel Beams | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4050 | Windows/Ex Doors - Mat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4051 | Windows/Ex Doors - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4060 | Skylight - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4061 | Specialty Glass - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4070 | Roofing - Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4071 | Roofing - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4080 | Plumbing - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4082 | Plumbing - Fixtures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4085 | Electrical - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4086 | Low Voltage - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4090 | HVAC - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4100 | Pre-Fab Fireplace - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4110 | Trash Removal - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4120 | Deck - Materials | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4121 | Deck - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4130 | Front Porch - Mat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4131 | Front Porch - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4140 | Siding/Cornice - Mat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4141 | Siding/Cornice - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4145 | Flashing - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4150 | Cedar Shingles - Mat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4151 | Cedar Shingles - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4170 | Shutters | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4180 | Insulation - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4190 | Flower Box - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4200 | Housewrap - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5010 | Sheetrock - Materials | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5011 | Sheetrock - Sub *** | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5020 | Garage Doors - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5030 | Drive/Walk/Patio - M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5031 | Drive/Walk/Patio - S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5035 | Public Walks - Conc | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5036 | Public Walks - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5045 | Lockout - Materials | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5046 | Lockout - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5049 | Trim - Materials | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5050 | Trim -Int Doors - Mat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5051 | Trim - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5055 | Stair Parts - Mat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5060 | Gutters - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5065 | Metal Roof - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5070 | Cabinets - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5075 | Countertops - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5080 | Paint - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5090 | Sinks / Tubs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5095 | Cultured Marble - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5100 | Fireplace Veneer - Mat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5101 | Fireplace Veneer - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5111 | Ceramic Tile - Sub *** | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5130 | Hardware/Supplies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5140 | Mirrors/Ecl/Shlve - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5150 | Light Fixtures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5160 | Appliances - Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5170 | Hardwoods - Sub *** | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5180 | Vinyl Flooring - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5190 | Carpet Flooring - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5200 | Screens - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5220 | Mailbox - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5230 | Wrought Iron - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5240 | Tub/Sink Repair - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5270 | Elevator - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6040 | Irrigation System - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6050 | Landscape - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6060 | Fence | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6070 | Window Clean - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6080 | Interior Clean - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6090 | Carpet Clean - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6100 | Pressure Wash - Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6110 | Labor Cleanup / Punchout | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7025 | Utilities - Water/Sewer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7050 | Pool, pavers, Fence | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7055 | Interior Upgrades | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7060 | Exterior Upgrades | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7080 | Design Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7082 | Sales Commission | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9999 | Transfer WIP to CGS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## ESTIMATE
7772 Turner Rd. ¦ Woodstock, GA 30188 ¦ (404) 867-7890
ESTIMATE |  |  |  | Estimate #
Estimate for |  | Payable to
Stone Column Properties, LLC.
7772 Turner Rd., Woodstock, GA 30188
Project
ESTIMATED COST CATEGORY | SCOPE / BASIS |  |  |  | ESTIMATED COST
Preconstruction & General | Estimated costs for preconstruction & general based on the current project budget and scope. |  |  |  | 0
Sitework | Estimated costs for sitework based on the current project budget and scope. |  |  |  | 0
Foundation | Estimated costs for foundation based on the current project budget and scope. |  |  |  | 0
Structure, Exterior & MEP | Estimated costs for structure, exterior & mep based on the current project budget and scope. |  |  |  | 0
Interior Finishes | Estimated costs for interior finishes based on the current project budget and scope. |  |  |  | 0
Exterior Improvements & Closeout | Estimated costs for exterior improvements & closeout based on the current project budget and scope. |  |  |  | 0
Other Project Costs | Estimated costs for other project costs based on the current project budget and scope. |  |  |  | 0
Cost-plus arrangement. Budget amounts are estimates only. Owner is billed for actual project costs incurred plus the stated project-management fee. |  |  | Estimated Hard Costs |  | 0
|  |  | Management Fee (18%) |  | 0
|  |  | ESTIMATED PROJECT TOTAL |  | 0
|  |  | Estimated Deposit |  | 0
Signature & Date:

## INVOICE
7772 Turner Rd. ¦ Woodstock, GA 30188 ¦ (404) 867-7890
INVOICE |  |  |  | INVOICE
Progress Draw 1
Bill to |  | Payable to
Stone Column Properties, LLC.
7772 Turner Rd., Woodstock, GA 30188
Project
ACTUAL COST CATEGORY | CURRENT ACTUAL COST |  | PRIOR ACTUAL COST |  | CUMULATIVE ACTUAL
Preconstruction & General | 0 |  | 0 |  | 0
Sitework | 0 |  | 0 |  | 0
Foundation | 0 |  | 0 |  | 0
Structure, Exterior & MEP | 0 |  | 0 |  | 0
Interior Finishes | 0 |  | 0 |  | 0
Exterior Improvements & Closeout | 0 |  | 0 |  | 0
Other Project Costs | 0 |  | 0 |  | 0
Cost-plus billing based on cumulative QuickBooks actual job costs. Current draw equals cumulative actual cost less actual costs billed on prior draws. Budget figures are estimates only and do not cap actual reimbursable costs. Payment terms: Due upon receipt |  |  | New Actual Costs |  | 0
|  |  | Management Fee (18%) |  | 0
|  |  | Gross Current Draw |  | 0
|  |  | Credit / Deposit Applied |  | 0
|  |  | AMOUNT DUE |  | 0
|  |  | Previously Billed incl. Fee |  | 0
|  |  | Cumulative Actual incl. Fee |  | 0
See INVOICE DETAIL for the cost-code reconciliation supporting this draw.

## INVOICE DETAIL
INVOICE DETAIL - ACTUAL COST RECONCILIATION
Invoice Detail
Code | Cost Category | Estimated Budget | QB Cumulative Actual | Previously Billed | Current Draw Cost | Variance to Budget
1010 | Plan / Site Plans | 0 | 0 | 0 | 0 | 0
1011 | Permits/Fees/Water/Sewer | 0 | 0 | 0 | 0 | 0
1020 | Surveys | 0 | 0 | 0 | 0 | 0
1070 | Builders Risk Insurance | 0 | 0 | 0 | 0 | 0
1080 | Reinspection Fees | 0 | 0 | 0 | 0 | 0
2010 | Grading - Clear Lot | 0 | 0 | 0 | 0 | 0
2011 | Grading - Haul Debris | 0 | 0 | 0 | 0 | 0
2012 | Grading - Cut Foundation | 0 | 0 | 0 | 0 | 0
2013 | Grading - Backfill Found | 0 | 0 | 0 | 0 | 0
2014 | Grading - Cut Drive | 0 | 0 | 0 | 0 | 0
2015 | Grading - Final | 0 | 0 | 0 | 0 | 0
2016 | Grading - Misc | 0 | 0 | 0 | 0 | 0
2021 | Retaining Walls - Sub | 0 | 0 | 0 | 0 | 0
2030 | Erosion Control | 0 | 0 | 0 | 0 | 0
2031 | Gravel | 0 | 0 | 0 | 0 | 0
3005 | Pump Concrete | 0 | 0 | 0 | 0 | 0
3010 | Footing - Material | 0 | 0 | 0 | 0 | 0
3011 | Footing - Sub | 0 | 0 | 0 | 0 | 0
3020 | Block - Materials | 0 | 0 | 0 | 0 | 0
3021 | Block - Sub | 0 | 0 | 0 | 0 | 0
3031 | Slab - Sub | 0 | 0 | 0 | 0 | 0
3050 | Foundation Wall - Material | 0 | 0 | 0 | 0 | 0
3051 | Foundation Wall - Sub | 0 | 0 | 0 | 0 | 0
3070 | Termite Treat Soil | 0 | 0 | 0 | 0 | 0
3080 | Waterproof Foundation | 0 | 0 | 0 | 0 | 0
3090 | Engineering | 0 | 0 | 0 | 0 | 0
3095 | Water Lines - Sub | 0 | 0 | 0 | 0 | 0
3096 | Sewer Lines - Sub | 0 | 0 | 0 | 0 | 0
4010 | Brick - Materials | 0 | 0 | 0 | 0 | 0
4011 | Brick - Sub | 0 | 0 | 0 | 0 | 0
4020 | Stone - Sub | 0 | 0 | 0 | 0 | 0
4021 | Stucco - Sub | 0 | 0 | 0 | 0 | 0
4030 | Framing - Material | 0 | 0 | 0 | 0 | 0
4031 | Framing - Sub | 0 | 0 | 0 | 0 | 0
4032 | Floor Screw - Sub | 0 | 0 | 0 | 0 | 0
4040 | Trusses - Material | 0 | 0 | 0 | 0 | 0
4041 | Steel Beams | 0 | 0 | 0 | 0 | 0
4050 | Windows/Ex Doors - Mat | 0 | 0 | 0 | 0 | 0
4051 | Windows/Ex Doors - Sub | 0 | 0 | 0 | 0 | 0
4060 | Skylight - Sub | 0 | 0 | 0 | 0 | 0
4061 | Specialty Glass - Sub | 0 | 0 | 0 | 0 | 0
4070 | Roofing - Material | 0 | 0 | 0 | 0 | 0
4071 | Roofing - Sub | 0 | 0 | 0 | 0 | 0
4080 | Plumbing - Sub | 0 | 0 | 0 | 0 | 0
4082 | Plumbing - Fixtures | 0 | 0 | 0 | 0 | 0
4085 | Electrical - Sub | 0 | 0 | 0 | 0 | 0
4086 | Low Voltage - Sub | 0 | 0 | 0 | 0 | 0
4090 | HVAC - Sub | 0 | 0 | 0 | 0 | 0
4100 | Pre-Fab Fireplace - Sub | 0 | 0 | 0 | 0 | 0
4110 | Trash Removal - Sub | 0 | 0 | 0 | 0 | 0
4120 | Deck - Materials | 0 | 0 | 0 | 0 | 0
4121 | Deck - Sub | 0 | 0 | 0 | 0 | 0
4130 | Front Porch - Mat | 0 | 0 | 0 | 0 | 0
4131 | Front Porch - Sub | 0 | 0 | 0 | 0 | 0
4140 | Siding/Cornice - Mat | 0 | 0 | 0 | 0 | 0
4141 | Siding/Cornice - Sub | 0 | 0 | 0 | 0 | 0
4145 | Flashing - Sub | 0 | 0 | 0 | 0 | 0
4150 | Cedar Shingles - Mat | 0 | 0 | 0 | 0 | 0
4151 | Cedar Shingles - Sub | 0 | 0 | 0 | 0 | 0
4170 | Shutters | 0 | 0 | 0 | 0 | 0
4180 | Insulation - Sub | 0 | 0 | 0 | 0 | 0
4190 | Flower Box - Sub | 0 | 0 | 0 | 0 | 0
4200 | Housewrap - Sub | 0 | 0 | 0 | 0 | 0
5010 | Sheetrock - Materials | 0 | 0 | 0 | 0 | 0
5011 | Sheetrock - Sub *** | 0 | 0 | 0 | 0 | 0
5020 | Garage Doors - Sub | 0 | 0 | 0 | 0 | 0
5030 | Drive/Walk/Patio - M | 0 | 0 | 0 | 0 | 0
5031 | Drive/Walk/Patio - S | 0 | 0 | 0 | 0 | 0
5035 | Public Walks - Conc | 0 | 0 | 0 | 0 | 0
5036 | Public Walks - Sub | 0 | 0 | 0 | 0 | 0
5045 | Lockout - Materials | 0 | 0 | 0 | 0 | 0
5046 | Lockout - Sub | 0 | 0 | 0 | 0 | 0
5049 | Trim - Materials | 0 | 0 | 0 | 0 | 0
5050 | Trim -Int Doors - Mat | 0 | 0 | 0 | 0 | 0
5051 | Trim - Sub | 0 | 0 | 0 | 0 | 0
5055 | Stair Parts - Mat | 0 | 0 | 0 | 0 | 0
5060 | Gutters - Sub | 0 | 0 | 0 | 0 | 0
5065 | Metal Roof - Sub | 0 | 0 | 0 | 0 | 0
5070 | Cabinets - Sub | 0 | 0 | 0 | 0 | 0
5075 | Countertops - Sub | 0 | 0 | 0 | 0 | 0
5080 | Paint - Sub | 0 | 0 | 0 | 0 | 0
5090 | Sinks / Tubs | 0 | 0 | 0 | 0 | 0
5095 | Cultured Marble - Sub | 0 | 0 | 0 | 0 | 0
5100 | Fireplace Veneer - Mat | 0 | 0 | 0 | 0 | 0
5101 | Fireplace Veneer - Sub | 0 | 0 | 0 | 0 | 0
5111 | Ceramic Tile - Sub *** | 0 | 0 | 0 | 0 | 0
5130 | Hardware/Supplies | 0 | 0 | 0 | 0 | 0
5140 | Mirrors/Ecl/Shlve - Sub | 0 | 0 | 0 | 0 | 0
5150 | Light Fixtures | 0 | 0 | 0 | 0 | 0
5160 | Appliances - Material | 0 | 0 | 0 | 0 | 0
5170 | Hardwoods - Sub *** | 0 | 0 | 0 | 0 | 0
5180 | Vinyl Flooring - Sub | 0 | 0 | 0 | 0 | 0
5190 | Carpet Flooring - Sub | 0 | 0 | 0 | 0 | 0
5200 | Screens - Sub | 0 | 0 | 0 | 0 | 0
5220 | Mailbox - Sub | 0 | 0 | 0 | 0 | 0
5230 | Wrought Iron - Sub | 0 | 0 | 0 | 0 | 0
5240 | Tub/Sink Repair - Sub | 0 | 0 | 0 | 0 | 0
5270 | Elevator - Sub | 0 | 0 | 0 | 0 | 0
6040 | Irrigation System - Sub | 0 | 0 | 0 | 0 | 0
6050 | Landscape - Sub | 0 | 0 | 0 | 0 | 0
6060 | Fence | 0 | 0 | 0 | 0 | 0
6070 | Window Clean - Sub | 0 | 0 | 0 | 0 | 0
6080 | Interior Clean - Sub | 0 | 0 | 0 | 0 | 0
6090 | Carpet Clean - Sub | 0 | 0 | 0 | 0 | 0
6100 | Pressure Wash - Sub | 0 | 0 | 0 | 0 | 0
6110 | Labor Cleanup / Punchout | 0 | 0 | 0 | 0 | 0
7025 | Utilities - Water/Sewer | 0 | 0 | 0 | 0 | 0
7050 | Pool, pavers, Fence | 0 | 0 | 0 | 0 | 0
7055 | Interior Upgrades | 0 | 0 | 0 | 0 | 0
7060 | Exterior Upgrades | 0 | 0 | 0 | 0 | 0
7080 | Design Fee | 0 | 0 | 0 | 0 | 0
7082 | Sales Commission | 0 | 0 | 0 | 0 | 0
9999 | Transfer WIP to CGS | 0 | 0 | 0 | 0 | 0